## Slide 1: Planning. Implementation and Evaluation of Health Education and promotion program
By: Dereje Geleta ( BSc, MPH)

## Slide 2: Learning objectives
After successful completion this of session students will be able to:
- Describe Planning
- Describe steps of planning in HEP
- Describe Precede-proceed model

## Slide 3: Planning in Health Education and promotion
Planning- is an anticipatory decision making about what needs to be done, how it has to be done, and with what resources.
It is central to health education and health promotion process

## Slide 4
Identify problems and prioritize (II)
Situational analysis (I)
Setting objectives (III)
Develop plan of work (IV)
Implementation (V)
Evaluation (VI)
Reconsideration (VII)
Steps of planning Health education and Promotion intervention.

## Slide 5: Step I. situational analysis
The local situation is the bench mark from where people should start the process of program planning.
After assembling the facts pertaining to local situations, it is important to analyze these facts in such away that they will be useful to individuals or planners.

## Slide 6: Information for situational analysis
The information collected may include:
Community and its topography
Demographic and socio-economic characteristics
Communication network
Cultural practices and their impact on health
Health beliefs and practices

## Slide 7: Step II. identify problems and prioritize
A number of problems are emerged out of needs assessment/situational Analysis.
Since it is not possible or feasible to deal with all the problems at once, we will have to prioritize

## Slide 8: Criteria to prioritize
1. Magnitude of the problem- How wide spread the problem is?
2. Severity of the problem – fatality, consequence, disability
3. Feasibility – in terms of time, resources, etc.
4. Government concern –Priority policy
5. Community concern – Felt need of the community

## Slide 9: Additional criteria
Immediate necessity
Number of people benefiting
Sustainability
Local leadership available for the task

## Slide 10
S/N | Problems | M | S | F | G | C | Total | Rank
1 | Malaria |  |  |  |  |  |  | 
2 | TB |  |  |  |  |  |  | 
3 | HIV/AIDS |  |  |  |  |  |  | 
4 |  |  |  |  |  |  |  | 
5 |  |  |  |  |  |  |  | 
6 |  |  |  |  |  |  |  | 
7 |  |  |  |  |  |  |  | 
Example of problem prioritization
Score each out of five

## Slide 11: Step III: Setting objectives
Once the problems have been prioritized, the next step is to set objective.
It is impossible to evaluate a course of action or a program efficiently without a clearly stated objective.
A program objective is a series of statement that must answer:
    What do we want to achieve?
    Where?
    Who is the target group?
    When do we want to achieve?
    Extent of achievement?

## Slide 12: For example, to increase immunization coverage from 60% to 90% among under 5 children in Hawassa City by 2020
What
Where
Who
When
Extent
In Hawassa City
Increase immunization coverage
Among under 5 year children
By 2020
From 60% to 90%

## Slide 13: Objective …
A specific objective should be SMART
S -Specific, simple- relates to a specific event, activity or impact
M -Measurable- has an indicator which is measurable
A - achievable- can be accomplished. bearing in mind the strengths, Weaknesses, opportunities & threats.
R -Realistic/relevant – can reduce or solve a problem relevant of the community
T - Time bound – can be accomplished in a specified period of time.

## Slide 14: Step IV. Develop plan of work
A plan of work is a detailed schedule of activities to be done in a given period of time.
It should specify the role of different persons involved, the time in which the particular activities have to be carried out, and the different methods to be used.

## Slide 15: Work plan…
In short, an action plan should answer the following questions.
When should it start and when should it be completed?
Who does it?
Who is responsible for seeing it is actually carried out?
What materials and resources are needed?

## Slide 16: Example
s/n | Activity | time | manpower | place | Budget | Monitor | Evaluation | 
1 | Assessment | 1st week of sept | 3researcher 1 mentor | Woreda “X” | 200000 ETB | TBA | quarterly | 
2 | training | 3rd week of Feb | 2 MPH | Hawassa | 500,0000 ETB | TBA | Daily | 
3 | Polio vaccination | 2nd week | 5 lab,2 nurse | “Y” woreda | 300,000 ETB | daily | weekly | 

## Slide 17: Planning Models used in Health Education
There are many planning model in health education and promotion.
Among these models, the Precede-Proceed model is the well known and most frequently used model to plan, implement and evaluate health education and promotion programs.
Developed by Lawrence W. Green and his colleagues in 1980

## Slide 18: The PRECEDE/PROCEED Framework Lawrence W. Green & Marshall W. Kreuter
PRECEDE
P = Predisposing
R = Reinforcing
E = Enabling
C = Causes
E = Educational
D = Diagnosis
E = Evaluation
PROCEED
P = Policy
R = Regulatory
O = Organizational
C = Constructs
E = Educational
E =Environmental
D = Development

## Slide 19: Cont …
Note: The two fundamental propositions which are emphasized by PRECEDE-PROCEED model are:
I. Health and health related risks are caused by multiple factors
II. Efforts to effect behavioral, environmental and social change must be multidimensional.

## Slide 20: PRECEDE-PROCEED MODEL Diagram
Quality of life
Phase 1
Social
Diagnosis
Health
Phase 2
Epidemiological
Diagnosis
Health
education
Policy
regulation
organization
Public
Health
Phase 5
Administrative & Policy Diagnosis
Phase 6
Implementation
Phase 7
Process evaluation
Phase 8
Impact evaluation
Phase 9
Outcome evaluation
Predisposing
Reinforcing
Enabling
Phase 4
Educational &
Ecological
Diagnosis
Behavior
Environment
Phase 3
Behavioral &
Environmental
Diagnosis
Green & Kreutzer, Health Promotion Planning, 3rd ed., 1999.

## Slide 21: PRECEDE has five phases-PLANNING PHASE
Phase 1: Social diagnosis
Phase 2: Epidemiological diagnosis
Phase 3: Behavioral and environmental diagnosis
Phase 4: Educational and organizational diagnosis
Phase 5: Administrative and policy diagnosis

## Slide 22: Phase 1 – Social Diagnosis
Phase 1: seeks to subjectively define the Quality of life (problems & priorities) of priority individuals or population needs & aspirations
Identify social problems that impact quality of life,
Identify health issues from people point of view
Quality of Life
Phase 1
Social diagnosis

## Slide 23: Phase 2 – Epidemiological Diagnosis
Determine Health issues associated with the quality of life.
e.g. Morbidity, Mortality, Risk factors, Disability, Incidence, prevalence of disease
Objective data is gathered, usually from secondary data sources / Epidemiological data
Creating priorities among the problem or list of problem
To identify health problems
Phase 2
Epidemiological Diagnosis

## Slide 24: Phase 3: Behavioral and Environmental Diagnosis
In phase 3, indentify behavioral and non-behavioral causes (environmental factors) which seem to be linked to health problems identified in Phase 2 and put them separately.
Phase 3: Behavioral and non-behavioral diagnosis
To identify
Behavioral and
Non-behavioral cause for the health problem

## Slide 25: Phase 4: Educational & Organizational Diagnosis
Identifies causal factors that must be changed to initiate and sustain the process of behavioral and environmental change identified in Phase 3.
Identify cause of behaviors
Educational Diagnosis
Organizational Diagnosis
1. Predisposing factors (knowledge, attitude, beliefs etc. )
2. Enabling factors (money, resource, time, accessibility, availability etc.)
3. Reinforcing factors (peer pressure )
Review the organizational objectives and focus on areas that facilitate changes

## Slide 26: Phase 5: Administrative and Policy Diagnosis
Focuses on administrative and organizational concerns which must be addressed prior to program implementation
Includes assessment of resources, budget development and allocation, development of implementation timetable, organization and coordination with others
Analysis of policies, resources and circumstances prevailing organizational situations that could hinder or facilitate the development of the health program Policy Diagnosis

## Slide 27: PRECEDE- phase ends with a Comprehensive Intervention plan which is ready for implementation and PROCEED begins
Design a Comprehensive Intervention plan
P
R
O
C
E
E
D
Ready made plan

## Slide 28: PROCEED has four phases:
Phase 6: Implementation
Phase 7: Process evaluation
Phase 8: Impact evaluation
Phase 9: Outcome evaluation

## Slide 29: Phase 6: Implementation
Beginning of PROCEED
The act of converting program objectives into actions through policy changes, regulation and organization.
It is translating the goals, objectives and methods into a community based health education programs.

## Slide 30: Phases 7 , 8, & 9 - Evaluation
Phase 7: Process evaluation - measurements of implementation process to control, assure, or improve the quality of the program
Phase 8: Impact evaluation - immediate observable effects of program (changes in Knowledge, attitude, beliefs, practice etc.)
Phase 9: Outcome evaluation -long-term effects of the program such as reduction in mortality, morbidity, prevalence of disease, improved health status, life expectancy

## Slide 31
Plan your work.
Work your plan.

## Slide 32: The End
THANK YOU !!