## Slide 1: Planning

## Slide 2: Outline
Definition
Features of planning
Types of planning
Steps of planning

## Slide 3: Session objectives
At the end of this session, you will be able to:
Define planning
Define health planning
Describe features of planning
Discuss types of planning
Explain steps of planning

## Slide 4: Brainstorming
What is planning?
Why is planning important?
What types of planning do you know?

## Slide 5: Health Planning
Planning is the combination of compiling and analyzing information, dreaming up ideas, using logic and imagination and judgment in order to arrive at a decision about what should be done.
Planning is deciding in advance what is to be done
It is projected course of action for the future
Planning is not simply a technical exercise; but it is an ongoing process of learning, adapting to change, and educating

## Slide 6: Cont …
It’s concerned with both ends (what) and means (how)
Specific objectives covering a specific time period are defined
These objectives are written and shared with organizational members to reduce ambiguity and create a common understanding about what needs to be done

## Slide 7: Cont …
A true plan should not be a static document
  A plan is not a plan if it is not dynamic, evolving with the changing environment.
A plan does not provide the ultimate solution but offers the mechanism for finding the solution.
  It should embody the principles necessary for achieving the goals of the community or the organization.

## Slide 8: Cont …
Rationale of planning
It provides direction to managers and non-managers
It reduces uncertainty by forcing managers to look ahead, anticipate change, consider the impact of change, and develop appropriate responses
Minimizes waste and redundancy

## Slide 9: Cont …
Establishes the goals or standards used in controlling
    Without planning, there would be no goals against which to measure work effort

## Slide 10: Cont …
Health Planning- is the process of defining community health problems, identifying needs and resources, establishing priority goals, and setting out the administrative action needed to reach those goals
Planning assumes future will be different from present
It is a device for change

## Slide 11: Cont …
Features of planning:
  Clear vision, mission, goal and objectives
  A clear picture of the tasks to be accomplished
  The resources needed to accomplish the task (human, material, financial, time…)
  Takes place at any level in health system & continually
  Needs participation of d/t government sectors, community, NGOs ….

## Slide 12: Cont …
Vision: is a picture of desired future of a country, an organization, an individual ….
  Enables people to play an active role in creating the future
  Describes where the group or the organization wants to be in the future
  Is a visual image you can see in your mind
E.g. ‘We see healthy children walking to school on safe roads’

## Slide 13: Cont …
Mission: is a statement which describes why the organization exists.
  Mentions the target population it serves
  Describes the services offered
  Scope of the organization’s activities
E.g. ‘Debre Birhan Hospital strives to provide preventive, promotive, curative, & rehabilitative health services to the people of Debre Birhan town and its surroundings so that the people lead a healthy and prosperous life.’

## Slide 14: Cont …
Types of planning
Based on scope and time of the plan, it is of two types:
Strategic/allocative planning
Is the process of determining what an organization intends to be in the future and how it will get there
It takes five years or more

## Slide 15: Cont …
Is comprehensive in scope, reflect long–term needs & directions of the organization.
Is a top management plan and focuses on overall organizational goal

## Slide 16: Cont …
2. Operational/tactical/activity planning
Are plans used to implement strategic plans
Short range planning that emphasizes on current operations of various parts of the organization
Are more limited in scope & address those activities and resources required

## Slide 17: Cont …
Deal more with the implementation & scheduling of actual work activities
Contains substantial amount of details

## Slide 18: Strategic vs. operational plans
Areas of differences | Strategic plan | Tactical plan
Individuals involved | Top level manager | middle/front-line
Facts to be based on | Facts are generally -difficult to gather | facts are generally- easy to gather
Amount of details | relatively little detail | Substantial detail
Time covered | long period (> 5yrs) | Short period (< 1yr)

## Slide 19: Cont …
Steps of planning
In the planning process, there are the following steps
Plan the planning
Review of policy guidelines
Situational analysis
Problem analysis & prioritization
Setting objectives and targets
Formulate interventions
Determine resource requirements
Preparing budget
Prepare action plan
Monitoring & evaluation
Writing the plan

## Slide 20: Cont …
1. Plan the planning
  This stage deals with prerequisites that have to be in place and issues that have to be resolved before actual planning exercise may start
  The objective is to ensure that planning process can be carried out smoothly
  Establish the identity and position of the planning body, i.e. the team

## Slide 21: Cont …
Determine specific terms of reference of the plan:
    what has to be planned?, the purpose of planning
    defining target group, for what time period
    identify resources available, timings, tasks and responsibilities
    assign responsibility to each member (chairman, secretary, core members, community representatives, from other government department, NGOs)

## Slide 22: Cont …
2. Review of policy guidelines
It is the process of familiarization with government directives and conditions that must be followed in preparation of the health plans
To ensure the health plan is in line with government national health policy

## Slide 23: Cont …
3. Situational analysis and problem identification
It is the stage of planning which implies understanding of current situation
It provides a common reference point for the rest of the planning process
It allows the selection of priority areas of concern for planning
Answers the question “where are we now?”
The current situation is described with identification of health and health related needs and available resources

## Slide 24: Cont …
Issues such as:
  Population characteristics
  Area characteristics & infrastructure
  Policy and political environment
  Health needs
  Organizational structure and functions of health services
  Resources (personnel, financial, material ….)
  Past implementation experience should be analyzed well

## Slide 25: Cont …
What are possible sources of data for situational analysis & problem identification?

## Slide 26: Cont …
Sources of information for situational analysis & problem identification
  Vital Statistics
  Census
  Health Information Systems
  Hospital Records
  Health System Review/System Analysis
  Community Surveys
  Qualitative Methods for Data Collection

## Slide 27: Cont …
4. Problem analysis and prioritization
Problem is a gap between current situation and desired future
Problem analysis is the art of critical examination of problems against prevailing conditions of your organization
The analysis is done by constructing a problem tree
A problem tree is a set of assumptions on causes associated with the problem and its consequences

## Slide 28: Cont …
When analyzing problems, we should define clearly what the problem is, find all possible causes of the problem, & not confuse ‘problems’ with ‘causes’
Root causes of a given problem should be analyzed well using methods such as 5 whys, fishbone analysis …..
Objectives, targets, and strategies should focus on root causes of the problem

## Slide 29: Cont …
E.g. Problem- high prevalence of diarrheal disease
  Possible causes: Inadequate and unsafe water supply, poor sanitary conditions, inappropriate weaning practice

## Slide 30: Cont…
Grouping of problems
A. Environmental problems
  Poor sanitary conditions
  Poor housing conditions
  Inadequate and unsafe water supply
  Air pollution and so on

## Slide 31: Cont …
B. Diseases/health problems
Malaria, tuberculosis, HIV/AIDS, malnutrition, respiratory diseases, etc
C. Socio-economic problems
  Low per capital income
  Low literacy rate
  Inequitable distribution of health services
  Cultural and religious beliefs and values

## Slide 32: Cont …
D. Health services problems
Poor quality and quantity of drugs
Old medical equipments
Lack of qualified personnel
Difficulty in visiting out-reach areas
Grouping helps seek common solutions to groups of problems

## Slide 33: Cont …
Problems are prioritized in the light of competing needs and limited resources.
Setting priority is, perhaps the most critical and hardest planning stage and yet cannot be avoided.

## Slide 34: Cont …
Criteria for problem prioritization
Magnitude of the problem: the public health burden imposed by the problem
Degree of severity: consequent suffering, death and disability
Feasibility: possibility of tackling the problem with available intervention

## Slide 35: Cont …
Community concern: how much does it relate to community perceived health needs?
Political expediency: if the problem is not recognized as politically expedient by the central authority, it is very difficult to include it among the high priority list
  The problem should be politically acceptable to convince local politicians

## Slide 36: Cont…
Based on the above criteria ranking is then done by using on 5 point scale
  very high (5), high (4), moderate (3), low (2) and very low (1)

## Slide 37: Cont …
5. Setting objectives and targets
Goals, aims, objectives and targets are all ways of describing the desired direction of a service.
They differ in terms of breadth and detail
Goals:- Are broad statements. There is generally one goal for a service.
  E.g. ' Health for all by 2000 and beyond.‘

## Slide 38: Cont …
Aims:- There are a number of aims relating to the goal. They are specific to particular health problems.
  E.g. 'To raise the nutritional status of women and children.‘
Objective:- For each programme aim, there may be a number of objectives which are specified in measurable terms.

## Slide 39: Cont …
An objective should be SMART i.e. specific, measurable, attainable, realistic, time bounded
Specific
  An objective must be specific with a single key result.
  If more than one result is to be accomplished, more than one objective should be written.
  Just knowing what is to be accomplished is a big step toward achieving it.
  Once you clarify what you want to achieve, your attention will be focused on the objective that you deliberately set.

## Slide 40: Cont …
Measurable
  Allows monitoring & evaluation
  Only an objective that affects behavior in a measurable way can be optimally effective.
  If possible, state the objective as a quantity.
  Avoid statements of objectives in generalities.
  Avoid infinitive verbs such as to know, to understand, to enjoy, and to believe.

## Slide 41: Cont …
  Action verbs are observable and better communicate the intent of what is to be attempted.
  E.g. To identify, to contrast, to select, to conduct, to compare, to investigate, and to develop.
  Attainable
    An objective must be attainable with the resources that are available.
    What barriers stand between you and your objective?
    How will each barrier be overcome and with what resource?

## Slide 42: Cont …
Realistic
  The objective should be central to the goals of the organization.
  The successful completion of the objective should make a difference.
  How will this objective help the organization move ahead?
  Is the objective aligned with the mission of the organization?

## Slide 43: Cont …
Time bound
  The objective should be traceable in time period.
  Specific objectives enable time priorities to be set and time to be used on objectives that really matter.
  Are the time lines you have established realistic?
  Will other competing demands cause delay?

## Slide 44: Cont …
  Will you be able to overcome those demands to accomplish the objective you've set in the time frame you've established?

## Slide 45: Cont …
Targets:- For each objective, there may be various targets which specify various points on the way to the attainment of the objective.
A target establishes a measured amount of output to be achieved in relation to a health objective through a specific program activity.
  Whereas objectives are set with respect to needs in the client population, targets are set with respect to service providers.

## Slide 46: Cont …
Example
Objective: By the end of 2012 E.C, 90% of antenatal clients shall be tested for syphilis in Arsi Negele town.
Targets
  Number of lab technologists to be trained
  Number of reagent to be available
  Number of health education sessions to be provided for ANC clients ….

## Slide 47: Cont …
6. Formulating interventions
Is a process of identifying, short-listing and deciding between alternative approaches and measures to address identified and prioritized health problems and needs.
‘’how will we get there?”
Steps
Identifying and short-listing gaps and weaknesses in existing service components

## Slide 48: Cont …
Identifying additional components and activities that are required to bring about the desired changes in the existing service components.
Identifying potential constraints and limitations to planned interventions.
Modifying proposed interventions in line with geographical, political, climatic and socio cultural conditions, including existing infrastructure, management and organization

## Slide 49: Cont …
Addressing constraints by using community resources, modifying job responsibilities and tasks, shifting available resources from one activity to another and obtaining additional resources;
Improving management and administration in line with identified interventions.

## Slide 50: Cont …
7. Determining Resource Requirements
Involves translation of interventions and all activities required into resources such as human labor, materials, money, space, time and information.
Specify existing resources, additional resources required and total resources needed.
To do this, list all programme activities, and the type and quantities of resources required by each programme activity.

## Slide 51: Cont …
8. Budget preparation
Preparing a budget implies conversion of inputs, activities, targets and support services into money.
The budget is made up of recurrent (ongoing/routine) and developmental (capital - fixed asset) costs within a period of time.

## Slide 52: Cont …
9. Preparing the Plan of Action
A plan of action is usually prepared in a matrix format and contains:
  The problem, objective(s), interventions
  Activities, inputs, key responsible actor/implementer
  Activity monitoring indicator
  Planned output
  Activity cost and implementation time frame.

## Slide 53: Cont …
10. Monitoring and Evaluation
The key question to be addressed at this stage of the planning cycle is “how will we know when we get there and what have we achieved ?”
Developing indicators
Identify means of verification

## Slide 54: Cont …
11. Writing Up the Plan
Purpose of writing a plan
  To carry out the work
  To request funds or resources from the government or funding agencies
  For monitoring & evaluating the implementation process by all concerned
A plan should include:
  1. Summary of main points
  2. Introduction (General background and Statement of the problem)

## Slide 55: Cont…
3. Objectives and targets should be clearly stated
4. Strategies & activities should be clearly stated using Gantt chart
5. Resources requirement
  The type and number of resources needed
  How each of the resources are going to be utilized
6. Monitoring & evaluation
  Mention how monitoring and evaluation is to be performed
  By whom?
  When?
  Indicators of effectiveness should be decided beforehand

## Slide 56: Cont …
Why plans fail?
Planning is not integrated into the total management system
A lack of understanding of the different steps of the planning process
Concerned parties not participated or contributed in the planning process
Management expects that plans will be realized with little effort

## Slide 57: Cont …
Too much attempted at once
Failing to operate by the plan
Inadequate input in planning
Unforeseen (unexpected) changes in the environment

## Slide 58: Group work
Assume you are a staff in a health center where the following problems are identified
Long acting family planning acceptance rate of 10%
Tuberculosis prevalence of 8%
Surgical site infection 30%
Skilled delivery of 50%
  Prioritize the problems and select two of them
  Set an objective for each problem
  Devise interventions
  Identify necessary resources
  Prepare budget
  Prepare plan of monitoring & evaluation