## Slide 1: University of Gondar Faculty of Education Department of Educational Planning and Management
Presentation on the course Education Project and Program Evaluation to 2nd year students in the 2019/20 academic year.
Birara Asnakew

## Slide 2: Chapter One: The Basics of Project and their Scope
1.1.Definitions of Project
The term project has a number of definitions.
A project is a set of investments and of other planned activities aimed at achieving specific objectives within a pre-determined time-frame and budget.
1.2.Project Organizations
Organizational environments are becoming complex and volatile.
This requires to set more viable strategies that will help to achieve best results economically and technologically.

## Slide 3: Cont’d
The more complex a task and unpredictable its environment is the greatest cooperation it claims between and amongst its departments.
Traditional organizations are less flexible in their task-expert arrangements as they are characterized by a split-up in between competence and management.
Project organizations are more flexible in the utilization of resources and decision making approaches.
In project organizations there is no single best option in structuring tasks and teams that perform them.

## Slide 4: Cont’d
While structuring them we need to consider the specific organizational conditions particularly the technological and social contexts.
Project management has to identify the internal and external requirements prior to the start of a project.
1.2.1.Project Organization and Responsibilities
The structural organization is a static framework that defines:
the internal distribution of tasks to individuals or departments,
and the relationship between the experts/departments.

## Slide 5: Cont’d
While the structural organization defines who has to do a job the operational structure follows a more dynamic approach, namely when, where and how often something has to be done.
In Project Management, the structural organization has to fulfill two tasks:
1. Definition, how a project organization is embedded within the parent organization (organizational models)
2. Definition, how the project organization is structured internally within the project team.

## Slide 6: Cont’d
There are two fundamentally different ways of organizing projects within the parent organization:
a. The project as part of the functional organization or pure line organization.
b. The project as a free-standing part of the parent organization (project organization)
a. In the pure line organization or functional organization:
There is no specific/distinct position for project managers
Experts and project manager are drawn from different units staffed in the line/functional organization.
Project managers are specialist or line managers who are assigned to the project for a specific time.

## Slide 7: Cont’d
The project is divided into partial tasks and delegated to responsible departments.
The team members continue to report to their line supervisors and upper managers.
b. Within the pure project organization ,an assigned project manager is fully responsible for a group of specialists who temporarily dedicate their entire work time to the project.
In this kind of project arrangement experts are temporarily hired until project is completed and autonomy of decision is at a better status.

## Slide 8: 1.3.Project stakeholders
Project stakeholders are individuals and organizations;
that are actively involved in the project or,
whose interests may be affected positively or negatively.
Key stakeholders on every project include:
1. Project manager—the individual responsible for managing the project.
2.Customer—the individual or organization that will use the project’s product/service.

## Slide 9: Cont’d
Performing organization—the enterprise whose employees are most directly involved in doing the work of the project.
Project team members—the group that is performing the work of the project.
Sponsor—the individual or group within or external to the performing organization that provides the financial resources, in cash or in kind for the project.
Factors that are leading to the increased use of project management .
Global competition
Knowledge explosion

## Slide 10: Cont’d
Corporate downsizing due to rigorous competition
Increased customer focus for services or products
Rapid development of Third World and closed economies. More and more project orgzns are existent
Major outcomes for the 21st century
An increase in the scope of project management and system integration.
The focus of projects has shifted from tactical to strategic.
An increasing discipline in the way projects are managed.

## Slide 11: Cont’d
Project management future trends
The growth and acceptance of PM are expected to continue well into the 21st century.
Significant growth are especially expected in the area of multinational PM
Project will be more dynamic and complex
Long term solution sought.
More efforts will be focused on teaching and training in the area of project management .

## Slide 12: 1.6.Management-by-Projects
In the beginning, its practice was limited to certain organization- engineering, construction, aerospace and defense for many years.
Now a days projects are influencing the tasks of every organization- both product and service rendering institutions.
The management-by-projects approach encourages:
Organization flexibility.
Decentralized management responsibility.
Holistic view of problems
Goal-orientated problem solution processes.

## Slide 13: 1.7. Projects in Education
In an education system there can be projects in the following areas.
The implementation of a new curriculum;
The computerization of an educational system;
Renovating teaching programs
The design of courses
Development of workshops for upper management levels.
Studying towards an academic degree.
Project-based teaching.

## Slide 14: The History of Educational Projects funded by Multilateral Development Banks
The execution of huge projects that influence national educational goals in the developing world has a historical underpinning.
Three phases can be discussed in this connection.
Educational Projects in the 1960s .
The main actors in sponsoring projects were multilateral banks.
These banks used to employ strict criteria to qualify the funding of projects initiated by different nations
Projects that emphasize on economic development were given priority in this connection.

## Slide 15: Cont’d
For example WB-financed projects were required to focus on;
vocational training and technical and agricultural education at all levels, and on the other hand,
general secondary education for developing scientific and technical streams.
The Inter-American Development Bank had a broader scope of intervention, extending in particular to university education as a whole.
The obvious absence from this list was primary education.

## Slide 16: Cont’d
The banks considered that their focus on expansion was mainly a response to social demand.
Throughout this period, expenditure financed by multilateral bank assisted projects included only the construction and equipment of school infrastructures.
Technical assistance, training scholarships, and more generally any expenditure related to intellectual investment were rarely considered by these banks.
When and if needed ,these costs were covered by UNDP.
Evaluation in the end showed only an increase in the expansion of secondary education, post-secondary education and vocational training without impacting quality and effectiveness.

## Slide 17: Projects in the 1970s
Projects to be initiated were also required to have social orientation unlike the previous one.
This is because projects in the sixties hardly showed improvements in the lives of the target beneficiaries-only created disparities.

## Slide 18: Cont’d
A growing proportion of their funding started to be allocated to social objectives:
nutrition
literacy
reducing infant mortality
increasing life expectancy
improving the productivity of small farmers, etc.
Four main objectives of greater importance depending on the funding organization were pursued this time:

## Slide 19: Cont’d
primary education, or, if classical primary education turned out to be too costly or ill-suited to the country's needs ,ABE was an option.
selective development of the subsequent levels of education and training to meet the demand for qualified manpower.
improvement of the effectiveness and quality of education;
equalization of opportunities of access to education.

## Slide 20: Cont’d
projects of the seventies encompassed all types and levels of education and ;
units responsible for educational planning,
pedagogical research
financial services and
education personnel.
With a view to selecting priority projects carefully, several multilateral banks asked borrowing states to carry out ;
a diagnostic study of their education system, encompassing its problems, its prospects and the government policy.

## Slide 21: Cont’d
This time, a large number of projects financed experimentation with or development of non-formal education like;
agricultural or crafts training,
adult literacy, in particular by using primary schools as development centers.
basic education patterns that would be less costly than classical primary education, and better suited to the conditions of disadvantaged rural areas and
They also funded studies like ;
development of new technological means such as radio or television

## Slide 22: Cont’d
construction and equipment continued to get lions share emphasis this time.
intellectual investment
(technical assistance and
training scholarships) projects used to have significant proportion.
Particular in this connection were;
curriculum development,
the production and distribution of school textbooks,
assistance with the planning and administration of education
experimentation with innovations, and
the carrying out of pre-investment studies.

## Slide 23: Cont’d
Evaluation of the performance of projects revealed ;
Intellectual investment out of Africa were observed to have a positive bearing on
the quality of education and
development of relevant national institutions.
Evaluations disclosed the failure of the many reforms or innovations supported by projects.
Particular cases in this regard were;
projects aimed at the development of non-formal education;
the idea of providing education in primary schools after class hours didn’t succeed as speculated.

## Slide 24: Cont’d
The provision of technical assistance and scholarships yielded positive results in several areas, especially technical education and the development of institutions.
Evaluations also revealed that the biggest problem was the difficulty for borrowing states, because of their other budgetary commitments.
Projects in the 1980s
Education projects financed with the support of multilateral banks were shaped by three main influences:
1. the impact of the world economic crisis on borrowing countries,
2. the results of projects during the previous decades, and
3. research work on education and development.

## Slide 25: Cont’d
This time former objectives were maintained
For primary education because of the severity of crisis-induced budgetary constraints efficiency was stressed.
Projects were often aimed at encouraging certain changes in national education policies, for example those regarding the allocation of budgetary resources for education, or the policy concerning scholarships.

## Slide 26: Relationship between Plans, Policies, Programs and Projects
Activity What is the relationship between and among these tools that guide organizational performance?

## Slide 27: Cont’d
Plans are inclusive of all the rest
Policies guide organizational direction.
Policies as broad guidelines of organization’s future destination need to be translated in to programs for implementation
However programs are broader in scope than projects.

## Slide 28: Project Scope
Activity
What is project scope?
How is it related to project goal?

## Slide 29: Scope of Projects
Defining the project scope sets the stage for developing a project plan.
Scope is related to the definition of the end result of the project.
Poor scope definition for major segments of the project has the greatest negative impact on cost and schedule.
Scope refers to the project purpose throughout the life of the project for the customer and project participants and this is reflected in the objectives.

## Slide 30: Project Parameters
Activity
What do we mean by project parameter ?
What are the parameters of a project?

## Slide 31: Cont’d
Every project is examined under such parameters as:
Scope:
establishes the boundaries of the project.
is a specification of the right function to be carried out in the project.
may change with changes in circumstances but detecting and adjusting it in time will be a challenge to be faced.

## Slide 32: Cont’d
b. Cost:
Is a major element in the management of a project
Comparing the actual occurrence of costs with the budgetary provision is a critical means of cost control.
c. Time:
Is the duration within which project activities individually and the total project will need to be completed.
It has an inverse relationship with a direct cost

## Slide 33: Cont’d
d. Resource:
consists of the physical facilities, materials; finance and human among others.
Project implementation should entertain efficiency
e. Quality:
Refers to both the final output and the process of implementation of the project.
Managing the project quality contributes not only to the quality of the final output but also to minimizing wastage and rework.

## Slide 34: Project classification
Activity
1. How are projects classified?

## Slide 35: Cont’d
Projects can have the following classification.
1. Small, medium, large.
2. Owner sponsored and externally sponsored.
3. High socio-economic value and low socio-economic value.

## Slide 36: Advantages and disadvantages of Project-based tasks.
1. What are the advantages and disadvantages of making tasks project-based?

## Slide 37: Cont’d
Advantages
It enhances logical structuring of elements.
it is possible to rationalize the implementation of development policies.
fragmentation of actions and clarification of their objectives make it easier to assess results and to learn lessons for the future.

## Slide 38: Cont’d- advantages
Resources can be gathered within a limited period of time for achieving a certain goal.
A certain problem can be solved more quickly and smoothly than in the usual regular line organization
Better coordination and cooperation in decision making can be achieved than in the line organization
Tasks in project have the involvement of experts with a better specialization.
Project justified problems have better level of acceptance than their initiation for their execution in the line organization.

## Slide 39: Cont’d- Disadvantages
b. Disadvantages.
As project planning is solely dependent on reliable, valid and current data , this sometimes become a huge burden.
Projects eliminate any coherence a plan might have, because of the fragmentation they introduce into its implementation.

## Slide 40: Cont’d -Disadvantages
In addition to this, the limitations of projects can be seen in the following angles.
They may require highly specialized skills for their planning, implementation and execution which the line organization may be required to incur additional costs for their fulfillment.
Execution costs are more exaggerated in projects than in the line organization
Projects create follow up problems for the line organization.
Because project may require the employment of new staff temporarily, it has little motivating effect on their performance.
Because projects may require the assignment of staff from diversified backgrounds, diversity management inflicts challenges to the project manager.

## Slide 41: Kinds of jobs that need project planning
Activity
What kind of organizational activities require the designing of implementation with the help of projects?

## Slide 42: Kinds of jobs that need project planning
The task is complicated and light must be shed from several directions.
The task is entirely new and when there is uncertainty about how to handle it.
The task involves several organizations and units and demands cooperation.
The task is cost intensive and requires a unique follow up mechanism.
The task is to be carried out within a definite period of time.
The task is limited and specified.
The task demands broad and active participation.

## Slide 43: Unit Two: Project Cycle Management
Activity
1.What do we mean when we say project management is a cyclic process? Why is project management a cyclic?
2. Discuss and suggest the processes of project development/phases of project planning.

## Slide 44: Cont’d- Project cycle management
The Meaning of Project Cycle
Projects in formal organizations are inherently cyclic processes.
Projects are increasingly becoming tools for coping up the challenges that organizations face due to technological and economic dynamism.
The results of one phase is the input of the next phase.

## Slide 45: Cont’d-Project cycle management
The following are considered to be important stages of the project cycle.
Idea conception and project identification
Project write up/formulation/preparation/design.
Project presentation, appraisal, selection, negotiation, approval.
Project implementation and management.
Project monitoring and supervision
Project evaluation

## Slide 46: 1. Idea conception and project identification
Activity
What does idea conception mean?
Who conceives project ideas?
What are the sources of project ideas?

## Slide 47: Idea conception and project identification
Project Ideas may arise from many area. They may emanate from :
Development plan-policy-strategy
Programming mission
As a follow-up to another project
External assistance agency agenda
Unused natural resources
Emergencies
A commercial initiative
Community urge

## Slide 48: 1. Idea Conception and Project Identification
Project planning begins with the conceiving of ideas or intentions.
Project idea conception is getting a hint about the project to be pursued.
. Under this phase there are two stages to pass through to identify the idea of the development project. They are:
a. Screening and Justification of the project
b. Project identification brief (PIB) or Concept note preparation.

## Slide 49: a. Screening and Justification of the project
Gaps in relation to a given felt need/conceived idea are examined through detailed needs assessment.
This helps to set a priority among the different problems prevailing to come up with a problem that is most critical to that particular target beneficiary.
Needs assessment should be participatory with the beneficiaries.
The assessment of needs can consider the following kinds of needs.

## Slide 50: Cont’d
Felt Needs: Perception of needs within a community/organization.
b. Normative Needs: These are needs as determined by :
External and international standards for desirable or acceptable conditions.
experts or professionals or policies defining what conditions are desirable or acceptable
c. Relative Needs:
The level of need in the proposed project area as compared with other areas measured against national standards.

## Slide 51: Cont’d
Typically, relative needs are assessed when a project is being identified at concept stage.
In general ,needs assessment:
Identifies and determines the scope of the social, economic, and environmental conditions or issues that need improvement.
Helps to generate information/data about the gap between the current status and desired level
Helps to confirm or negate conditions for further action.
Helps to define goals and objectives

## Slide 52: Cont’d
ensures goals and objectives are aligned with the organization’s strategic plan and other planning documents;
identifies stakeholders and potential collaborators.

## Slide 53: Cont’d
After needs are examined and problems sifted, there follows;
analysis of the problems that are given greater weight.
Questions that might be addressed this time include:
What are the nature and scope of the problem? Where is the problem located, whom does it affect, and how does it affect them?
What is it about the problem or its effects that justifies new, expanded, or modified projects or programs?
What feasible actions are likely to significantly ameliorate the problem?
Who are the stakeholders and sponsors?

## Slide 54: Cont’d
The needs assessment shows us the breadth of the situation in a target area/organization,
but the problem analysis provides us with a tool to go more deeply into the underlying causes and effects of specific problems.
Problem analysis is especially important because;
it makes people think about what their most important problems are.
This helps to prioritize projects amidst limited resources.
it ensures that if the right cause of the problem is identified, then the right solution can be found.

## Slide 55: Cont’d
There are several steps to undertake within problem analysis, including:
1. Writing the problem statement
2. Determining Problems, their causes and consequences.
3. Prioritizing and selecting the causes and consequences to be addressed.
4. Using Problem analysis tools to identify leverage points (i.e. those areas where you are likely to have the most impact)
5. Identifying the potential interventions and tie everything together into a logic statement.

## Slide 56: Cont’d
What are problems, causes and consequences?
Problems
A problem is a specific negative situation related to a an organization ,dep’ts or group’s well-being.
Eg . Students’ low achievement.

## Slide 57: Cont’d
Causes
Causes are the contributing factors for the existence of the problem.
There are two levels of causes:
underlying causes
root-causes.
a. Underlying causes are:
those that are most visible and recalled first in the process of problem analysis.
can be considered in multiple dimensions of cause and effect.
For example, when inspecting the underlying causes for increased pregnancy rate among teenage girls, a conclusion could be drawn that women do not use birth control mechanisms.

## Slide 58: Cont’d
The underlying cause for this fact could be that they do not have access to contraceptives, or that they have never been educated on how to use contraceptives.
Underlying causes can be explored by continuing to ask “why” until the root-cause is identified.
b. Root-causes are:
identified by analyzing the problem to its core.
those that give the last possible explanation of the existing problem.
If a “why” question fails to yield an answer for an underlying cause, then that problem reached is a root cause and this is the problem that requires project intervention.

## Slide 59: Cont’d
Consequences are social, environmental, political or economic conditions that result from the problem.
For example, some consequences of a high pregnancy rate among teenage girls are increased:
maternal morbidity and mortality rates,
rate of school drop outs
unemployment among young people etc.

## Slide 60: Stakeholder analysis
What does stakeholder mean?
What is the importance of stakeholder analysis to our project? What are their areas of contribution?
Consider a preparatory school in your area. What are its stakeholders?

## Slide 61: Cont’d
Stakeholders Analysis
A stakeholder is:
Any person, group, or organization that is interested to take part in matters that affect its reason of existence or goal.
The entire range of stakeholders for any given project can be fairly broad and often it is difficult to completely identify the group.
Nevertheless, the main stakeholders should be identified at the beginning of the project design and may include:
young people.
community and religious leaders,

## Slide 62: Cont’d
Politicians
teachers
service providers
employers
small businesses
NGOs
government organizations and institutions.

## Slide 63: Cont’d
stakeholders’ analysis is important :
to gain an understanding of which organizations or groups of people have an interest in the issues
To know what their interest is,
To know the ones that have the same goals you have
To know the ones that can help the project and the areas of their help
To mark the ones that have a negative influence and be a barrier for the project, and where within the planning process this information can be leveraged.

## Slide 64: Project Design Hierarchy and Planning Frameworks
The next task after problem analysis is following Project Design Hierarchy and fulfillment of planning Frameworks for a complete project planning.
The project design hierarchy is a logical structure, showing the relationship between resources, activities, and desired results.
If objectives are achieved goals can be achieved
If outputs are produced objectives can be achieved
If activities take place outputs can be produced.
If inputs are available activities can take place.

## Slide 65: Cont’d
Each level of this hierarchy is linked to the one below through the question “how?”
The relationship between goals, objectives, outputs, activities and inputs can be presented as follows.
E.G. Goal: Reduction of students’ dropouts.
How?
Objective: Improved awareness creation of the parents.
How?
Outputs: Parents trained through the organization of training.

## Slide 66: Cont’d
How?
Activities: a. Preparation of training modules
b. Organizing TOT
After reaching at this level, the next step is developing a summary of the main ingredients of the project with the help of a planning framework- Logframe.
Logframe describes all levels of the project, including activities and inputs, with indicators, targets, and assumptions; together with a monitoring and evaluation plan.

## Slide 67: Project Hierarchy or Logframe Definitions
A logfram contains the following elements.
The project logic: goal, objectives, outputs
The indicators, targets, and methods of measurement to determine whether the logic is effective
The work plan with activities and inputs
The critical assumptions behind the project design.

## Slide 68: Cont’d
Goal: Main overall purpose that the project will achieve usually framed as a sustainable improvement in human conditions or well being.
Objective: Major changes or results that need to be achieved to make an impact on the problem.
Output: Needed in order to achieve objectives. These are often defined as results of project interventions or sets of activities.
Activity: Actions carried out as part of an intervention.
Input: Resources used to carry out an activity or series of activities.

## Slide 69: Cont’d
Activities and inputs usually are included in a work plan rather than in the planning framework (logframe or results framework).
The log frame asks a series of further questions:
Where do we want to be? (GOAL, objectives)
How will we get there? (OUTPUTS, ACTIVITIES)
How will we know when we have got there? (INDICATORS)
What will show us we have got there? (EVIDENCE)
What are the potential problems along the way? (ASSUMPTIONS)

## Slide 70: Project Goals, Objectives, Outputs and Activities
Establishing the Goal of the Project
The first step in designing a project is to formally recognize and then state what the overall purpose of the project is; this is the goal.
This helps to address what has been identified as the problem.
A Goal represents:
ultimate aim or purpose of the project improvement in human condition
expected changes after interventions have been completed.

## Slide 71: Cont’d
Goals are not attained within short period time.
Eg. Improve community participation in decision makings in educational affairs.
    Establishing Objectives for the Project
    Are stepping stones to achieving the project goal.
    Are achieved in a relatively short period of time than goals.
    Objectives represent an elimination or reduction in the factors that have been identified in the problem analysis as the key underlying causes of the problem.

## Slide 72: Cont’d
Objectives:
Reflect the intended changes in systemic conditions
Should have measurable indicators which show what, when, and how conditions, behaviors, and practices will change
Must be verifiable at some point during the execution of the project.
Should continue to be met even after the completion of the project.

## Slide 73: Cont’d
Example of objectives:
Increased rate of parents who involve in school decision making in educational matters.
b. Improved rate of parents who began to work with teachers in relation to students cases
    Establishing Outputs
    Outputs are the direct results of the project interventions e.g. ( No of trainings, No of ToTs trained, Modules prepared etc)
    To determine outputs ask the mechanisms for addressing objectives

## Slide 74: Cont’d
    Establishing Activities
    should be outlined in the logframe or described in a work plan or Gantt chart, but must still be carefully thought out and planned during the project design process.
    Activities are specific actions carried out to achieve outputs
    For example, if training is the intervention, the activities may comprise 1) development of a training curriculum, 2) field testing message and training materials, 3) training of trainers, 4) identifying training participants, 5)implementation and completion of the actual trainings, 6) monitoring quality of training, etc

## Slide 75: Cont’d
Establishing Inputs
Inputs are resources used to implement activities.
These include field staff, facilities, equipment, or money
If training is the intervention, for each activity you should think of the critical inputs that will be needed.
. These can include the materials, trainers, venue, and logistical support.

## Slide 76: What is an Indicator?
are the measurements that show how and by how much a project is achieving its intended results
An example of an indicator is:
Percentage of children between the ages 7 and 14 and who are registered to attend primary education in the target area by the end of 2005.
    Kinds of Indicators
    are many types
    Can have such category as Formative and Summative

## Slide 77: Cont’d
FORMATIVE indicators(also called Milestones or a significant event) :
are used during an activity, phase or project to show whether progress is on track.
b. SUMMATIVE indicators
are used at the end of the project for evaluation.
Indicators can also be classified as :
Direct: measure the objective directly, such as the number of children attending school
only be measured after the project has ended.

## Slide 78: Cont’d
Indirect: (also called Proxy indicators) are used if direct indicators are not appropriate or possible.
Are used when:
Results cannot be measured directly, such as quality of life.
Direct indicators are too expensive to measure. For example to measure an increase in literacy it might be difficult or costly to interview children, but the number of books borrowed from the school library might give you an indication of whether or not literacy has increased.

## Slide 79: Cont’d
Indicators can also be classified as
Quantitative: This might include:
How often things happen
number of people involved or affected
growth rates
Uptake, for example, school enrolment, visits to clinic, adoption of new seed varieties.
b. QUALITATIVE indicators measure things that cannot be counted, like:

## Slide 80: Cont’d
satisfaction, opinions
decision-making ability
Changes in attitude.
Technical Characteristics of Targeted Indicators
Indicators should technically have the following features.
a. Specific : Is it clear in terms of what, how, when, where and who the situation will be changed?
Measurable: Are the targets measurable (for example, how much of an increase for how many people, over what length of time)?
Area-Specific : Does the statement delineate an area (village, province, agricultural zone) and/or a population group (sex, age, occupational group)?
Realistic: Is the project able to obtain the level of involvement and change reflected in the statement?
Time-bound: Does the statement reflect a time period in which it can reasonably be accomplished?

## Slide 81: Project Identification Brief (PIB) or Concept note preparation.
The PIB is a short summary about the need of intervention to mitigate the problem discovered
This document is instrumental to get the approval of project sponsoring units or bodies to get approval for the next task of the project cycle that is project preparation.

## Slide 82: 2.2.Project write up/formulation/preparation/design
Once a project is identified, the process of preparation is initiated.
This process involves the refinement of the elements described in the identification phase and includes all the steps that are necessary to bring the project to the stage of appraisal, which would consist of prefeasibility and feasibility studies.
A project Proposal may have the following structure and components
Title page
Title page should indicate

## Slide 83: Cont’d
the project title
the name of the lead organization (and potential partners, if any)
the place and date of project preparation and the name of the donor agency/dep’t to whom the proposal is addressed.
2. Project Title
The Title is the label of your submission and the most-read element.
It should be brief as few words as possible (<20), and informative:

## Slide 84: Cont’d
The project title should be short, concise, and preferably refer to a certain key project result or the leading project activity.
The title must be easy to understand
Project titles that are too long or too general fail to give the reader an effective snapshot of what is inside.
Following is an example of effective and ineffective titles.
a. Effective project titles
■ A Project Proposal on Raising Environmental Awareness to Students in the Non-governmental Primary Schools of Kebele Twenty
b. Ineffective titles
■ Environmental Education

## Slide 85: Cont’d
3. Abstract
Many readers lack the time needed to read the whole project proposal.
It is therefore useful to PLACE a short project summary termed as abstract.
The abstract should include:
the problem statement;
the project’s objectives;
implementing organizations;
key project activities; and
The total project budget.

## Slide 86: Cont’d
Theoretically, the abstract should be compiled after the relevant items to be treated in the proposal are prepared in their detailed form.
For a small project the abstract may not be longer than 10 lines.
Bigger projects often provide abstracts as long as two pages.

## Slide 87: Cont’d
4. Project Context
This part of the project describes the social, economic, political and cultural background from which the project is initiated.
It should contain relevant data from research carried out in the project planning phase or collected from other sources.

## Slide 88: Cont’d
5. Project justification
This is the rationale for the project.
Due to its importance usually this section is divided into four or more sub-sections
5.1. Problem statement
The problem statement provides a description of the specific problem(s) the project is trying to solve, in order to “make a case” for the project.
The project proposal should point out why a certain issue is a problem for the community or society as a whole, i.e. what negative implications affect the target group.
There should also be an explanation of the needs of the target group that appear as a direct consequence of the described problem.

## Slide 89: Cont’d
5.2. Priority needs
The needs of the target group that have arisen as a direct negative impact of the problem should be prioritized.
An explanation as to how this decision was reached (i.e. what criteria were used) must also be included.
For example, if the problem is stated as “… poor infrastructure in the community” the list of needs associated with this problem may be:

## Slide 90: Cont’d
improved water supply in quality and quantity;
better roads; and
Improved solid waste collection.
This procedure provides credibility to the selected intervention.

## Slide 91: Cont’d
5.3. The proposed approach (type of intervention)
The project proposal should describe the strategy chosen for solving the problem and precisely how it will lead to improvement.

## Slide 92: Cont’d
5.4. The implementing organization
This section should describe the capabilities of your organization by referring to its capacity and previous project record.
Describe why exactly your organization is the most appropriate to run the project, its connection to the local community, the constituency behind the organization and what kind of expertise the organization can provide.
If other partners are involved in implementation provide some information on their capacity as well.

## Slide 93: Cont’d
6. Project goal
7. Project results(Outcome and Output)
8. Target group
Define the target group and show how it will benefit from the project.
The project should provide a detailed description of the size and characteristics of the target groups, and especially of direct project beneficiaries.
The criteria for target group analysis may be ethnic composition, gender, age, etc.

## Slide 94: Cont’d
9. Project implementation
The implementation plan should describe activities and resource allocation in as much detail as possible.
It is exceptionally important to provide a good overview of who is going to implement the project’s activities, as well as when and where their implementation is.
The implementation plan may be divided into two key elements: the activity plan and the resource plan.

## Slide 95: Cont’d
  9.1. Activity plan (schedule)
The activity plan should include specific information and explanations of each of the planned project activities.
The duration of the project should be clearly stated, with considerable detail including the beginning and the end of the project.

## Slide 96: Cont’d
  9.2.Resource Plan
The resource plan should provide information on the means necessary to undertake the project.
Cost categories are established at this stage in order to aggregate and summarize the cost information for budgeting.

## Slide 97: Cont’d
10. Budget
In simple terms, a budget is an itemized summary of an organization's expected income and expenses over a specified period of time.
It is essential that financial officers comply clearly and punctually with a funding organization's budgeting and reporting requirements.
The two main elements of any budget are income and expenditures.

## Slide 98: Cont’d
11. Monitoring and evaluation
The basis for monitoring is set when the indicators for results are set.
The project proposal should indicate:
how and when the project management team will conduct activities to monitor the project’s progress;
Which methods will be used to monitor and evaluate; and who will do the evaluation.

## Slide 99: Cont’d
12. Reporting
The schedule of project progress and financial report could be set in the project proposal.
Often these obligations are determined by the standard requirements of the donor agency.
The project report may be compiled in different versions, with regard to the audience they are targeting.

## Slide 100: Cont’d
13. Management and personnel
A brief description should be given about the
project personnel
individual roles each one has assumed and
communication mechanisms that exist between them.

## Slide 101: 14. Annex
The annexes should include all the information that is important, but is too large to be included in the text of the proposal.
The usual documentation to be annexed with the project proposal is:
analysis related to the general context (e.g. a civil society sector assessment);

## Slide 102: Cont’d
Policy documents and strategic papers (e.g. a local environmental action plan)
information about the implementing organization/s (e.g. annual reports, success stories, brochures and other publications)
Additional information on the project management structure and personnel (curriculum vitae for the members of the project team); maps of the location of the target area.

## Slide 103: 2.2. Project Feasibility Study.
Preparation stage should be followed by the prefeasibility phase
The prefeasibility study is one of the two components of appraisal, the feasibility study being the other one.
This is the first attempt to examine the overall potential or viability of the project.

## Slide 104: Cont’d
The data used here are the ones gathered during preparation phase.
This is critical and ushers the culmination of the preparatory work providing comprehensive review about the project.
The prefeasibility study is the stage for completing all the preliminary steps for going into a detailed feasibility exercise.

## Slide 105: Cont’d
Its aim is to analyze the viability of a proposed project- product or service.
The Feasibility Study may produce a cost and benefit report and a project charter to be used as a guide during the analysis phase.
Feasibility is examined against the following standards.

## Slide 106: Cont’d
Technical feasibility. Here :
How technically suitable/appropriate the project is examined.
If for instance there is a construction project, is the construction appropriate enough to achieve the objectives set.
If the project relates to machines, the existence of electric power, experts that can operate etc can be considered

## Slide 107: b. Socio-Political Feasibility
Projects should be socially and politically acceptable.
Prior sensitization and information of the interested parties to get social and political acceptance is needed.
c. Administrative feasibility.
This significantly relates to the capacity for project implementation.

## Slide 108: Cont’d
the complexity of the project is well adapted to existing or potential administrative abilities.
d. Institutional feasibility.
How the institutions created and the changes introduced are sustainable is examined
How change sought from the project is to continue after the project's completion is the attention here.

## Slide 109: e. Financial feasibility
Many education projects have suffered in the past from under-estimation of the financial resources needed for their implementation.
How adequate the resource allocated is scrutinized and other options are set in case of financial strains.
  2.3.Project presentation, appraisal, selection, negotiation, approval.
  2.3.1. Financing Projects.
  This is the stage where the finance needed to execute the project is approved .
  This is the approval of the project either by accepting the project as it is or reduction of some amount

## Slide 110: 2.3.2. Project Appraisal
is the process assessing and questioning proposals before resources are committed.
Project appraisal is a requirement to be passed through before funding of programs is done.
This is a rigorous process where strong evaluation criteria about hr profitability of the project are used by an a relatively independent party.
What can Project Appraisal Deliver?
Project appraisal helps project initiators and designers to;
Be consistent and objective in choosing projects
Make sure their program benefits all sections of the organization
Provide documentation to meet financial and audit requirements and to explain decisions to interested parties.

## Slide 111: Cont’d
The following are thus the perceived benefits of appraisal to the organization that initiated the project and the party sponsoring the project.
Appraisal justifies spending money on a project.
Appraisal is an important decision making tool.
This helps ensure that projects selected for funding:
Will help a partnership achieve its objectives
Are deliverable
Involve local people and take proper account of the needs of people from ethnic minorities and other minority groups
Are sustainable
Have sensible ways of managing risk.

## Slide 112: Cont’d
Appraisal lays the foundations for delivery.
This means that appraisal helps ensure that :
projects will be properly managed, by ensuring appropriate financial and monitoring systems.
2.3.3. Negotiating Projects
This process confronts representatives of the organization that initiated the project and those of the funding body (the financiers)
This time the latest version of the project (for example, the appraisal report) is examined in detail.

## Slide 113: Cont’d
Appraisal may propose modifications.
During negotiation, power is in the hands of the financing body as they are owners of the resource.
      2.3.3.1.Preparing for negotiations
      Success during negotiation is the result of advance preparation.
      If there is haste during this process, it is often better to put off the date, rather than participating in it.
      Four points are essential for good negotiation preparation:
a. Knowing the project well;
b. Knowing the goals to be achieved and the admissible margin of flexibility;
c. Knowing the other partner,
d. Exploring possible areas of agreement.

## Slide 114: Cont’d
Experienced negotiators :
strive to develop in advance the arguments supporting their proposals.
restrict oneself to a small number of clear, solid arguments, if possible based on figures.
obtain as much information as possible about their future partners' point of view, motivation and pursued objectives.
  2.4. Project implementation and management.
  During this phase project leaders and project teams are involved with the following components:
  1. Team :comprised of people who have various backgrounds
  2. Goal :The project goal is sometimes vague or less firmly established.
  In many projects, it is necessary to adapt the goal as the project proceeds.

## Slide 115: Cont’d
Limited resources :No project is completely free of resource pressures.
Uncertainty (risk):
One characteristic feature of projects is that their success is never guaranteed beforehand.
Even if the desired goal is already being reached, it is uncertain whether it will be achieved within the available budget or the proposed time
Whatever a project manager does, it relates to the following five parameters:
Time
Money
Organization

## Slide 116: Cont’d
d. Quality
e. Information
These five parameters are often known as the ‘control factors’,
The control factors appear in project plans, progress monitoring and project reporting.
The five project parameters and their implication during project planning, progress monitoring and project reporting is discussed as follows.
Time
Managing time involves ensuring that tasks are completed on time.
Time in project plans:

## Slide 117: Cont’d
Determine which activities should take place in which phase.
Estimate how long each activity will take
Determine the order in which activities should be completed.
Allocate people and materials.
Determine the (most important) deadlines
Time in progress monitoring:
Monitor progress.
Monitor deadlines
Adjust schedules
Time in project reporting:
Report on the actual timeline.
Analyze and explain why some tasks proceeded much more quickly or much more slowly than expected.

## Slide 118: b. Money
The management of money within a project involves ensuring that the costs remain within the budget.
Money in project plans:
Determine the fees of the team members
Estimate the hours for the team members.
Assign budgets to team members for specific tasks.
Determine costs for material and tools.
Money in progress monitoring
Monitor cash flow
Negotiate with suppliers.

## Slide 119: Cont’d
Determine whether the original cost estimates are still accurate.
Adjust budgets
Negotiate with customer and/or client concerning budget adjustments.
Money in project reporting:
Compile financial reports and statements.
Analyze definitive financial report.
C. Quality
The project result must fulfill a number of quality requirements.
This also applies to the various intermediate products of the project.

## Slide 120: Cont’d
When managing a project, it is particularly important for quality requirements to be determined, agreed upon and recorded in writing during the definition phase.
Quality has a lot to do with meeting specifications set for each element of the project.
Additional quality requirements may be specified for various tasks within the project.
For example, a particular task can be carried out only by certified personnel.
Quality in project plans:
Establish the desired quality of the project result and the intermediate products (this takes place primarily in the definition phase).
Establish the desired quality for the accomplishment of the various activities in the project.

## Slide 121: Cont’d
Quality in progress monitoring:
Test the (intermediate) results.
Address any quality problems.
Quality in the project reporting:
Confirm that the desired quality has been attained.
Address any complaints (particularly in the follow-up phase).
Perfectionism impedes project management.
A pragmatic attitude toward the quality levels of a project can be expressed as ‘Good enough is good’.
Projects that strive to achieve the highest possible level of quality are often at great risk of never being completed.

## Slide 122: Cont’d
d. Organization.
Organization in project plans:
Assemble the team.
Assign authority.
Assign tasks to team members.
Make agreements concerning the availability of people with other (project) managers and higher management.
Organization in progress monitoring:
Direct the team.
Monitor human aspects (soft skills).
Mediate between the parties who are involved in the project.

## Slide 123: e. Information
The information factor concerns how, by whom and on which basis decisions can be taken.
Questions such as:
Who may decide about which matters in the project?
Is it the project leader, the client or a substantive expert within the team?
What will be archived and by whom?
Will tools (e.g. project website, issue tracker, e-mail notification, and joint agenda) be used?
These and other informational questions must be answered before a project can be started.

## Slide 124: Cont’d
Information in project plans:
Which information must be provided to whom and in which form?
Which information will be recorded, distributed and archived?
Which information tools will be used?
Information in progress monitoring:
Arrange for periodic consultation.
Ensure that the right information is provided to the right person.
Determine whether agreements have been met.
Information in project reporting:
Write the project report.

## Slide 125: 2.4.1. Planning Project Implementation
What is Project Implementation?
It is a process whereby “project inputs are converted to project outputs”.
May be looked at as:
Putting in action the activities of the project.
Putting into practice what was proposed in the project document (i.e. transforming the project proposal into the actual project.)
Management of the project or executing the project intentions.

## Slide 126: Cont’d
Project implementation planning involves:
Project activation:
This is making arrangements to have the project started.
It involves coordination and allocation of resources to make project operational.
2. Project operation
This is practical management of a project.
Here, project inputs are transformed into outputs to achieve immediate objectives.
The approaches to project implementation can be:
Top-down approach
Implementation is mainly done by agencies from outside the community with limited involvement by the beneficiaries.

## Slide 127: Cont’d
b. Bottom-up approach
Beneficiaries implement the project.
Outside agencies may provide the financial resources and technical assistance.
c. Collaborative/ participatory approach
Both top-down and bottom-up approaches to project implementation are applied in the process.
Project implementation plan includes:
a. The project implementation schedule
This is concerned with:
What activities can produce expected project outputs?
What is the sequence of these activities?
What is the time frame for these activities?
Who will be responsible for carrying out each activity?

## Slide 128: Cont’d
Project implementation plan includes the following methods:
1. Gantt chart
2. Critical Path Method (CPM) or Net work analysis.
3. Project Evaluation and Review Techniques (PERT)
4. Simple formats
1. GANTT Chart?
The Gantt chart is also referred to as the progress chart.
It is a chart showing the timing of project activities using horizontal bars.
It is one of the techniques of project scheduling, which depicts the frequency of activities and determines the time period for implementation.

## Slide 129: Cont’d
Procedures that need to be followed for preparing Gantt chart are as follows.
Determine the parts or implementation phases of the project and the sequence in which the associated activities shall be carried out
Then estimate the amount of time required for each activity
List the activities that can be carried out at the same time and identify those to be carried out sequentially.
Time represented on the horizontal axis, and activities on the vertical axis.
Bars indicate the time period allocated for each activity and the state of progress at any particular point in time.

## Slide 130: b. The role of the implementing agency
The specific responsibilities of the key staff during project implementation and monitoring are outlined.
c) Beneficiary participation
The involvement of the beneficiaries in planning and implementation and what is expected of them is spelt out.
d) Organizational structure and staffing
Here the following are sought:
Project structure for purposes of management.
Qualifications and skills needed for the staff.
Job descriptions and specifications for the staff.
Technical assistance if needed.

## Slide 131: Cont’d
e. Financial management
This looks at funds management, accounting period, financial reports and statements and how often they will be made?
f. Reporting system
This looks at who will be reporting to whom and how often. There is a need to design standard reporting formats.

## Slide 132: Cont’d
g. Sustainability
The concept of sustainability is based on the belief that project should result in benefits that have lasting effect.
Project should be sustained beyond the life of funding.

## Slide 133: Cont’d
Factors affecting project implementation
a. Factors that lead to success of projects
Political Commitment
Simplicity of Design
Careful preparation
Good management
Involvement of beneficiaries/community
b. Factors that lead to failure of projects
Financial Problems
Management problems
Technical problems
Political problems

## Slide 134: 2.5. Project Monitoring and Evaluation. 2.5.1. Project Monitoring
Project monitoring is an integral part of day-to-day implementation management
It provides information with which management can;
identify and solve implementation problems, and
assess progress.
The project elements that provide the basis for monitoring are:
The Logical Framework
the implementation schedule and
the activity and resource schedules

## Slide 135: Cont’d
The following basic issues need to be regularly monitored:
Which Activities are underway and what progress has been made (e.g. at weekly intervals)?
At what rate are means being used and cost incurred in relation to progress in implementation (e.g. monthly)?
Are the desired Results being achieved (e.g. quarterly update)? (efficiency)
Are the results addressing needs?
To what extent are these results furthering the Project Purpose (e.g., half-yearly analysis)? (effectiveness)
What changes in the project environment occur? Do the assumptions hold true?

## Slide 136: Cont’d
Monitoring can be carried out using two kinds of indicators.
Means or input indicators
for example, expenditure disbursed, the number of metric tons of cement used, technical assistance services in man-months;
Output indicators: for example, the number of square meters constructed or individuals trained the unit cost of construction or training, pupil enrolment, class repetition rate.

## Slide 137: Cont’d
Experience shows that project monitoring has not always been effective.
The main shortcomings appear to be;
lack of manager motivation,
excessive complexity and cost of the monitoring system, or
inadequate integration of this system in the project.

## Slide 138: 2.5.2. Project Evaluation
Evaluation is the systematic collection of information about:
activities,
characteristics, and
outcomes of projects
Evaluation helps to make:
judgments about the project,
improve effectiveness, and/or
inform decisions about future programming.

## Slide 139: Cont’d
Evaluation is not merely the accumulation and summary of data and information about a project.
Depending on the timing of the evaluation the following evaluation types can be distinguished
Mid-term evaluation:
are usually undertaken at mid-term to review progress and propose alterations to project design during the remaining period of implementation.
b . Final or end-of-project evaluation: objective is to;
document the resources used, results and progress towards objectives.
generate lessons about the project which can be used to improve future designs.

## Slide 140: Cont’d
c. An ex-post evaluation:
is conducted several years after completion of the project
often focuses on impact.
Such an impact (or lack of it) will also indicate to what extent the project results have proven to be sustainable.

## Slide 141: Unit Three: Project Management 3.1. Project Cycle Management and its Principles
Project Cycle Management is the term used to describe:
the management of activities and decision-making procedures
The management of key tasks, roles responsibilities and key documents.
PCM brings together organizational management principles and analytical tools and techniques to ensure that:
Projects are relevant to the agreed strategy and to the real needs of beneficiaries.
Projects are feasible

## Slide 142: Cont’d
Projects are sustainable.
PCM principles
Decision-making criteria and procedures are defined at each phase, including key information requirements and quality assessment criteria.
The phases in the cycle are progressive – each phase should be completed for the next to be tackled with success (with the exception of monitoring, which is a continuous process).
New programming and project identification draws on the results of monitoring and evaluation as part of a structured process of feedback and institutional learning.

## Slide 143: The Project Management Process
A process is a way of doing something that has the character of recurrence.
Project management is an integrative endeavor—an action, or failure to take action, in one area will usually affect other areas.
Project processes are performed by people and generally fall into one of two major categories:
Project management processes:
Describe, organize, and complete the work of the project.
Product-oriented processes.
Specify and create the project’s product.

## Slide 144: Cont’d
Project management processes can be organized into five groups.
Initiating processes—authorizing the project or phase
Planning processes—defining and refining objectives and selecting the best of the alternative courses of action to attain the objectives
Executing processes—coordinating people and other resources to carry out the plan.
Controlling processes—ensuring that project objectives are met by monitoring and measuring progress regularly
Closing processes—formalizing acceptance of the project or phase and bringing it to an orderly end.

## Slide 145: Skills and competencies of project Managers
a. Inspires a Shared Vision
An effective project leader is often described as having a vision of where to go and has the ability to articulate it.
Visionaries thrive on change and are able to draw new boundaries.
Visionary leaders enable people to feel they have a real stake in the project.
b. Good Communicator
Project leadership calls for clear communication about goals, responsibility, performance, expectations and feedback.

## Slide 146: Cont’d
The leader must have the ability to effectively negotiate and use persuasion when necessary to ensure the success of the team and project.
c. Integrity
a project leader must remember his or her actions but not words for the team.
Good leadership demands commitment to and demonstration of, ethical practices.
In other words the leader "walks the talk" and in the process earns trust.

## Slide 147: Cont’d
d. Empathy :
is considering others problems as ones own.
This is different from sharing feelings-sympathy
e. Competence
Manager knows what he or she is doing.
The manager should be versed in the area he is leading.
Expertise in leadership skills is another dimension in competence.

## Slide 148: Cont’d
f. Ability to Delegate Tasks
This refers to empowering fellow colleagues
Empowerment is a logical extension of trust
Trust is an essential element in the relationship of a project leader and his or her team.
"A good leader is a little lazy."

## Slide 149: Cont’d
g. Cool Under Pressure
we don't live in a perfect world - projects have problems.
When leaders encounter a stressful event, they consider it interesting, they feel they can influence the outcome and they see it as an opportunity.
never let others see you sweating.

## Slide 150: Cont’d
h. Team-Building Skills
Projects are exceedingly team ventures.
The leader must know the appropriate leadership style to use during each stage of team development.
i. Problem Solving Skills
Project management confront with a number of problems.
Managers thus have a "fresh, creative response to here-and-now opportunities," and not much concern with how others have performed them.

## Slide 151: Success Factors for Managing Projects
The success of a project is affected by internal and external factors:
Internal factors:
E.g. the number and skills of people needed to make a project work properly, can be controlled by the project.
b. External factors:
E.g. economic conditions (market, price) or the ecological conditions (climate, drought), cannot be controlled by the project.

## Slide 152: Cont’d
Project planners have to try to reduce the number of external factors that can negatively affect the project.
Thank you!