## Slide 1: Chapter-Five
Cost control and monitoring

## Slide 2: Introduction
In countries like Ethiopia most construction projects didn’t completed with the estimated project cost because of the following reasons:
  Variations due to request from either parties,
  Delay,
  Under estimated quantities,
  Incompleteness of designs,
The method of cost controlling in PPA has been defined from clause 37 up to 54 of General conditions of contract.

## Slide 3: Cost Control
Clause 37 : Bill of Quantities or activity schedule
  Types of Contract
    Admeasurements contract » BOQ
    Lump sum » Activity schedule
  The quantities set out in the Bill of Quantities are the estimated quantities for the Works, and they are not to be taken as the actual and correct quantities of the Works to be executed by the Contractor in fulfilment of his obligations under the Contract.
Clause 38: Change in bill of quantities
  Option 1: Changes in the Bill of Quantities for Admeasurements Contracts
    If final qty >qty in BOQ by 25% provided that the change exceeds 5% of the contract price, the engineer shall adjust the unit rate.
    The engineer shall not adjust the unit rate if the change exceeds 15% of the contract price.
    The contractor shall submit the cost breakdown up on request

## Slide 4: …Continued
  Option 2: Changes in the Activity Schedule for Lump Sum Contracts
    Prices in the Activity Schedule shall not be altered.
Clause 39: Variations
      All Variations shall be included in updated program produced by the Contractor
      Clause 40: Payment for Variations
      For both Admeasurement and Lump Sum Contracts, the Contractor shall provide the Engineer with a quotation for carrying out the Variation when requested to do so by the Engineer.
      For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities and if, in the opinion of the Engineer, the quantity of work above the limit stated in Sub-Clause 38.1 or the timing of its execution do not cause the cost per unit of quantity to change, the rate in the Bill of Quantities shall be used to calculate the value of the Variation

## Slide 5: …Continued
      If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work.
      For both Admeasurement and Lump Sum Contracts, if the Contractor’s quotation is unreasonable, the Engineer may order the Variation and make a change to the Contract Price, which shall be based on the Engineer’s own forecast of the effects of the Variation on the Contractor’s costs.
      For both Admeasurement and Lump Sum Contracts, if the Engineer decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event
      For both Admeasurement and Lump Sum Contracts, the Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning.

## Slide 6: …Continued
Clause 41: Cash flow forecast
  When the Program is updated, the Contractor shall provide the Engineer with an updated cash flow forecast.
Clause 42: Payment Certificates
  The Contractor shall submit to the Engineer monthly statements of the estimated value of the work executed less the cumulative amount certified previously
  The Engineer shall check the Contractor’s monthly statement and certify the amount to be paid to the Contractor.
  The value of work executed shall be determined by the Engineer.

## Slide 7: …Continued
  The value of work executed shall comprise the value of:
    The quantities of the items in the Bill of Quantities completed in the case of Admeasurement Contracts; or
    Completed activities in the Activity Schedule in the case of Lump Sum Contracts.
  The value of work executed shall include the valuation of Variations and Compensation Events.
  The Engineer may exclude any item certified in a previous certificate or reduce the proportion of any item previously certified in any certificate in the light of later information.

## Slide 8: …Continued
Clause 43: Payments
  Payments shall be adjusted for deductions for advance payments and retention
  If an amount certified is increased in a later certificate or as a result of an award by the Adjudicator or an Arbitrator, the Contractor shall be paid interest upon the delayed payment as set out in this clause
  Unless otherwise stated, all payments and deductions will be paid or charged in the proportions of currencies comprising the Contract Price.
  Items of the Works for which no rate or price has been entered in will not be paid for by the Employer and shall be deemed covered by other rates and prices in the Contract

## Slide 9: …Continued
Clause 44: Compensation event
Clause 45: Tax
  Unless otherwise specified in the SCC, the Engineer shall not adjust the Contract Price if taxes, duties, and other levies are changed that subsequently affect the Contract Price.
Clause 46: Currencies
  Where payments are made in currencies other than Ethiopian Birr, the exchange rates used for calculating the amounts to be paid shall be the exchange rates stated in the Contractor’s Bid.

## Slide 10: …Continued
Clause 47: Price Adjustements
  Price Adjustments formula
Clause 48: Retention
Clause 49: Liquidated damage
Clause 50: Bonus
Clause 51: Advance Payment
Clause 52: Securities
Clause 53: Day work
Clause 54: Cost of repair